## Scope
scope_id | deliverable | product | market | operator_owner_role | starts_on | access_expires_on
SC-01 | Pack-dropout recovery decisioning on the operator's CRM extract | Customer Intelligence | KE | CVM director | 2026-09-21 | 2026-12-15
SC-02 | Three-ledger reconciliation on monthly billing, charging and provisioning extracts | Revenue, Risk and Assurance | KE | Revenue assurance manager | 2026-09-21 | 2026-12-15
SC-03 | Runbook, training and monitoring for both capabilities | AI Assurance, Governance and Handover | KE | Head of data platform | 2026-09-21 | 2026-11-30

## Readiness
prerequisite_id | prerequisite | state | blocking | owner_role
RD-SPONSOR | Executive sponsor named and available fortnightly | met | yes | CTIO
RD-DATA | Read access to the CRM and billing extracts in a non-production environment | partial | yes | Head of data platform
RD-SECURITY | Security review of the pod's access and tooling signed | missing | yes | CISO
RD-ENV | A sandbox environment the pod can deploy to | met | no | Platform lead
RD-TEAM | Two operator engineers assigned for handover | partial | no | Head of data platform

## Milestones
milestone_id | week | scope_id | deliverable | acceptance_gate | accepts_role | state | evidence_filed
M1 | 2 | SC-01 | Data contract agreed for the CRM extract | Extract validated against the contract with zero structural refusals | CVM director | accepted | yes
M2 | 4 | SC-01 | Decisioning running on the sandbox extract | Ten decisions reviewed and agreed by the CVM team | CVM director | accepted | no
M3 | 6 | SC-02 | Reconciliation of one closed month | Finance confirms at least one exception | Revenue assurance manager | in_progress | no
M4 | 9 | SC-02 | Exception workflow with maker-checker | Two exceptions closed through the workflow | Revenue assurance manager | planned | no
M5 | 11 | SC-03 | Runbook and monitoring | Operator engineers run one full cycle unaided | Head of data platform | planned | no
M6 | 12 | HANDOVER | Handover | Every scope item accepted with evidence; access revoked | CTIO | planned | no

## Manifest
Key | Value
schema | heuritel.engagement-plan
version | 1
template | heuritel.engagement-plan.template
templateVersion | 1
engine | heuritel.engagement-plan.engine
engineVersion | 1
scenario | engagement-readiness-plan
market | engagement-readiness-plan-sample
marketVersion | 1
currency | KES
tenant | heuritel-public-sample
issuedAt | 2026-09-18
language | en-GB
Do not edit this sheet. | It identifies the pack when you send it back.

## Guide
Engagement readiness and plan — what this pack holds
Scope: what the pod delivers: a capability, a market, the owner on your side, the access it needs and when that access ends
Readiness: the prerequisites the pod depends on, scored, and whether each blocks the start
Milestones: the plan: week, deliverable, the gate it must pass, who accepts, the state, and whether evidence is filed
The engine assesses readiness (a missing blocking prerequisite means the plan cannot start), checks the plan (every scope item has a milestone with a gate; handover comes last; access expires on or after it), measures progress by accepted milestones with evidence filed, and states what handover acceptance still needs.
An accepted milestone without evidence filed is not counted as accepted.
Nothing here schedules work, grants access or accepts anything.
From the product's design workbook (12_Telecom_AI_Team_as_a_Service.xlsx, sha256 57ec14a7d91e…)
Promise: A bounded multidisciplinary team delivering inside the operator boundary (Data and template!A2)
Buyer: CTO/CDO (Data and template!B4)
Primary dataset: backlog, delivery and acceptance (Data and template!B5)
Operator systems: client repo, CI/CD, service management (Data and template!B6)
Primary measure: Accepted releases and lead time (Data and template!B7)
Data boundary: Operator-controlled subject_key only; no reversible mapping in workbook (Data and template!B9)
Editing rules
Change values, not the layout. Do not add, remove or reorder columns or sheets.
Do not use formulas. Paste values instead; a workbook with formulas is refused.
Money is whole units of the market currency, never cents. Dates are YYYY-MM-DD.
A subject column holds your own pseudonymous reference — never a phone number, IMSI, IMEI or account number.
Guide, Data_Dictionary, Validation_Lists, Expected_Outputs and Manifest are written by HeuriTel. Send them back unchanged.

## Data_Dictionary
Sheet | Column | Label | Type | Required | Allowed | Meaning
Scope | scope_id | Scope id | text | yes |  | Your own id, e.g. SC-01.
Scope | deliverable | Deliverable | text | yes |  | The capability delivered, in one phrase.
Scope | product | Product | text | yes |  | The HeuriTel product it draws on.
Scope | market | Market | text | yes |  | A market code.
Scope | operator_owner_role | Operator owner (role) | text | yes |  | The role on your side that accepts it — never a name.
Scope | starts_on | Engagement starts on | date | yes | YYYY-MM-DD | The date week 1 counts from.
Scope | access_expires_on | Access expires on | date | yes | YYYY-MM-DD | When the pod's access to this scope's systems ends.
Readiness | prerequisite_id | Prerequisite id | text | yes |  | Your own id, e.g. RD-SPONSOR.
Readiness | prerequisite | Prerequisite | text | yes |  | What must be in place, in one phrase.
Readiness | state | State | enum | yes | met ¦ partial ¦ missing | met, partial or missing.
Readiness | blocking | Blocks the start | boolean | yes | yes ¦ no | yes when the plan cannot start without it.
Readiness | owner_role | Owner (role) | text | yes |  | Who closes it, by role.
Milestones | milestone_id | Milestone id | text | yes |  | Your own id, e.g. M1.
Milestones | week | Week | integer | yes | 1 to 52 | Week of the engagement.
Milestones | scope_id | Scope id | text | yes |  | The scope item it delivers; HANDOVER for the handover milestone.
Milestones | deliverable | Deliverable | text | yes |  | What is handed over at this milestone.
Milestones | acceptance_gate | Acceptance gate | text | yes |  | The test that must pass, in one phrase.
Milestones | accepts_role | Accepts (role) | text | yes |  | The operator role that accepts.
Milestones | state | State | enum | yes | planned ¦ in_progress ¦ delivered ¦ accepted ¦ rejected | planned, in_progress, delivered, accepted or rejected.
Milestones | evidence_filed | Evidence filed | boolean | yes | yes ¦ no | yes when the evidence pack for this milestone is in the register.

## Validation_Lists
Rule | Requirement
scope.key | Scope: every scope_id is present and unique.
readiness.key | Readiness: every prerequisite_id is present and unique.
readiness.state | Readiness.state is one of: met, partial, missing.
milestones.key | Milestones: every milestone_id is present and unique.
milestones.week | Milestones.week is between 1 and 52.
milestones.state | Milestones.state is one of: planned, in_progress, delivered, accepted, rejected.
TAAS-R1 | Every milestone names a scope item on the Scope sheet or HANDOVER; exactly one milestone is HANDOVER.

## Expected_Outputs
Output | Label | Meaning
readiness | Readiness | prerequisites met, partial, missing; whether the plan can start.
plan | Plan check | scope covered, gates present, handover last, access expiry consistent.
progress | Progress | milestones accepted with evidence over milestones planned.
handover | Handover acceptance | what is still needed before the operator's owner can accept.